## Pending
Project Tracking
Priority Level |  | Critical | High |  | Middle |  | Low
Urgency Level |  | Critical | High |  | Middle |  | Low
Impact Level |  | Critical | High |  | Middle |  | Low
Pending
No. | Description |  |  | Impact Level | Priority | Urgency | Status | Owner | QA | Date | Complete Date
1 | 投票功能阻止冒泡事件 |  |  | High | High | High | In Progress | Lu, Guangwei | Zhang,Hongwei | 2016-01-14 | 2016-01-14
2
3
4
5
6
7
8
9
10
11
12
13
14
15

## In Progress
Project Tracking
Priority Level |  | Critical | High |  | Middle |  | Low
Urgency Level |  | Critical | High |  | Middle |  | Low
Impact Level |  | Critical | High |  | Middle |  | Low
In Progress
No. | Description |  |  | Impact Level | Priority | Urgency | Status | Owner | QA | Date | Complete Date
1 | 活动、发现 - 详情页面 |  |  | Middle | Middle | Middle | 80% | Hu, Dandan | Zhang,Hongwei | 2016-01-14
2 | IOS版本重新打包测试 |  |  | N/A | N/A | N/A | Done | Hu, Dandan | N/A | 2016-01-14
3 | 资产管理 - 借书，还书流程 |  |  | Middle | Middle | Middle | 30% | Lu, Guangwei | N/A | 2016-01-14
4 | 云服务器租赁 |  |  | Middle | Middle | Middle | 100% | Xi, Jie | N/A | 2016-01-14 | 2016-01-14
5 | 年会服务器 - 扩展及咨询 |  |  | Middle | Middle | Middle | 100% | Xi, Jie | N/A | 2016-01-14 | 2016-01-14
6 | 资产管理 － 主页 |  |  | Middle | Middle | Middle | Done | Lu, Guangwei | N/A | 2016-01-15 | 2016-01-18
7
8
9
10
11
12
13
14
15

## Bug
Project Tracking
Priority Level |  | Critical | High |  | Middle |  | Low
Urgency Level |  | Critical | High |  | Middle |  | Low
Impact Level |  | Critical | High |  | Middle |  | Low
Bug
No. | Description |  |  | Impact Level | Priority | Urgency | Status | Owner | QA | Date | Comments
1 | 投票页面 - 不能删除 |  |  | High | High | High | Open | Jin,L | Wu, Fan | 2016-01-15 | 后台接口没有定义
2 | 发起投票 - 选项可以输入超过40字 |  |  | Middle | Middle | Middle | In progress | Lu, Guangwei | Wu, Fan | 2016-01-15
3 | 发起投票 - 投票之后，返回投票页面，投票状态没有变为已投票 |  |  | High | High | High | Open | Jin,L | Wu, Fan | 2016-01-15
4 | 活动集锦点赞 - 点赞最后一个人名后面有“、” |  |  | Low | Low | Low | Done | Zhang, Huaifei | Wu, Fan | 2016-01-15
5 | 活动集锦 - 回复框，光标在回复提示的前面 |  |  | Low | Low | Low | Open | Lu, Guangwei | Wu, Fan | 2016-01-18 | 资产页面完成后修复
6 | 活动定位 - 点击定位查看活动地址（Tsidi 12F），地图不能打开 |  |  | High | High | High | Open |  | Wu, Fan | 2016-01-18 | 后台的数据填写规范准确即可
7 | 活动集锦 - 点击更多>>,会出现收起，没有"<<" |  |  | Low | Low | Low | Done | Lu, Guangwei | Wu, Fan | 2016-01-18 | 资产页面完成后修复
8 | 活动集锦 - 发布新的活动之后，页面不显示活动 |  |  | Middle | Middle | Middle | Open | Lu, Guangwei | Wu, Fan | 2016-01-18 | 资产页面完成后修复
9 | 项目案例页面 - 点赞：不能被点赞或者点赞出现负数 |  |  | High | High | High | Done | Hu, Dandan | Wu, Fan | 2016-01-18
10 | 项目案例及项目详情页面点赞 - 部分项目在项目案例页面的点赞数目与其项目详情页面的点赞数不同（例2015年的永辉项目） |  |  | Middle | Middle | Middle | Done | Hu, Dandan | Wu, Fan | 2016-01-18
11 | 项目案例及项目详情页面点赞 - 在项目详情页面点赞后，点击项目案例进入项目案例页面，该页面点赞数不能随之变化 |  |  | Middle | Middle | Middle | Done | Hu, Dandan | Wu, Fan | 2016-01-18
12 | 图片显示 - 部分项目图片读取太慢，图片显示不出来（例2013年的项目案例） |  |  | High | High | High | Open | Hu, Dandan | Wu, Fan | 2016-01-18 | 性能优化问题, 需要与后台讨论接口实现
14 | 项目详情页 - 在图片右下角出现“灰色圆张”（例2015年 Motorola Mobility Inc） |  |  | Low | Low | Low | Open | Hu, Dandan | Wu, Fan | 2016-01-18 | 用户体验
15 | 项目案例 - 16 17年的项目数据没有 |  |  | Middle | Middle | Middle | Open | Hu, Dandan | Wu, Fan | 2016-01-18 | 后台数据没有提供
16
17
18
19
20
21
22

## Done
Project Tracking
Priority Level |  | Critical | High |  | Middle |  | Low
Urgency Level |  | Critical | High |  | Middle |  | Low
Impact Level |  | Critical | High |  | Middle |  | Low
Done
No. | Description |  |  | Impact Level | Priority | Urgency | Status | Owner | QA | Date | Complete Date
1 | 有的投票选项没有内容，点击发起投票，出现错误提示，但是发起投票可以成功提交，并显示成功发送提示 |  |  | N/A | N/A | N/A | Fixed | Lu, Guangwei | Wu, Fan | 2016-01-15
2 | 选择图片显示超出范围 |  |  | N/A | N/A | N/A | Fixed | Lu, Guangwei | Wu, Fan | 2016-01-15
3 | 发现页面 - 不能评论 |  |  | N/A | N/A | N/A | Fixed | Lu, Guangwei | Wu, Fan | 2016-01-15
4 | 发现页面 - 从广场页面和我的页面时，点击发现页面，发现页面不显示动态 |  |  | N/A | N/A | N/A | Fixed | Lu, Guangwei | Wu, Fan | 2016-01-15
5 | 活动集锦签到 - “更多”、“收起”失效 |  |  | N/A | N/A | N/A | Fixed | Zhang, Huaifei | Wu, Fan | 2016-01-15
6 |  |  |  | N/A | N/A | N/A |  |  | N/A | N/A
7 |  |  |  | N/A | N/A | N/A |  |  | N/A | N/A
8 |  |  |  | N/A | N/A | N/A |  |  | N/A | N/A
9 |  |  |  | N/A | N/A | N/A |  |  | N/A | N/A
10 |  |  |  | N/A | N/A | N/A |  |  | N/A | N/A
11 |  |  |  | N/A | N/A | N/A |  |  | N/A | N/A
12 |  |  |  | N/A | N/A | N/A |  |  | N/A | N/A
13 |  |  |  | N/A | N/A | N/A |  |  | N/A | N/A
14 |  |  |  | N/A | N/A | N/A |  |  | N/A | N/A

## Planned
Project Tracking
Priority Level |  | Critical | High |  | Middle |  | Low
Urgency Level |  | Critical | High |  | Middle |  | Low
Impact Level |  | Critical | High |  | Middle |  | Low
Planned
No. | Description |  |  | Impact Level | Priority | Urgency | Status | Owner | QA | Date | Start Date
1 | 消息推送通知 -- App显示 |  |  | Low | Low | Low | Investigation | Hu, Dandan | N/A | 2016-01-13
2 | IOS 版本更新提示 -- Update in App Store |  |  | Low | Low | Low | Investigation | Hu, Dandan | N/A | 2016-01-14
3 | 团队风采页面 - 设计 |  |  | Low | Low | Low | Planned |  | N/A
4 |  |  |  | Low | Low | Low
5 |  |  |  | Low | Low | Low
6 |  |  |  | Low | Low | Low
7 |  |  |  | Low | Low | Low
8 |  |  |  | Low | Low | Low
9 |  |  |  | Low | Low | Low
10 |  |  |  | Low | Low | Low
11 |  |  |  | Low | Low | Low
12 |  |  |  | Low | Low | Low
13 |  |  |  | Low | Low | Low
14 |  |  |  | Low | Low | Low
15 |  |  |  | Low | Low | Low