## Summary
dLife Project Summary
User Story: Case management |  |  | Impact Level |  | Critical | High | Middle | Low
|  |  | Priority Level |  | Critical | High | Middle | Low
|  |  | Urgency Level |  | Critical | High | Middle | Low
Progress of Last Week |  |  | In This Week [Till Wednesday] |  |  | Plan for Next Week
User Stories | Opened | 34 | User Stories | Opened | 16 | Establish general interface for [Resources]
| In Progress | 4 |  | In Progress | 5 | Discuss interface for data migration O2O - dLife
| Pending | 2 |  | Pending | 3 | Investigate IOS features for dLife App
| Complete | 28 |  | Complete | 8 | Migrate data onto dLife TV
Combine [Sandbox] & [dLife TV]
Optimize user experiences

## Pending
Pending
User Story | Priority | Status | Case Owner | Assign To | Assign Date | Comments
消息推送后，在app端显示消息提示 | Low | Investigation | Xi,jie | Zhang,Huaifei | 2016-01-13
IOS:版本更新后,可以提示更新app | Low | Investigation | Xi,jie | Hu,Dandan | 2016-01-14

## In Progress
In Progress
User Story | Priority | Status | Case Owner | Assign To | Assign Date | Comments
活动、发现 - 详情页面 | High | 95% | Xi,Jie | Hu,Dandan | 2016-01-14
资产管理 - 借书，还书流程 | High | 85% | Xi,Jie | Hu,Dandan | 2016-01-14
投票页面目前不能删除投票 | Middle | 10% | Xi,Jie | Jin,Liang | 2016-01-18

## Complete
Complete
User Story | Priority | Status | Case Owner | Assign To | Assign Date | Comments
IOS版本重新打包测试 | High | 100% | Hu, Dandan | N/A | 2016-01-14 | 已打包
云服务器租赁 | High | 100% | Xi, Jie | N/A | 2016-01-14 | 已发送给Evan
年会服务器 - 扩展及咨询 | High | 100% | Xi, Jie | N/A | 2016-01-14 | 已发送给Evan

## Bug
Bug
User Story | Impact | Priority | Urgency | Status | Case Owner | Assign To | QA | Assign Date | Confirmation
发起投票:选项可以输入超过40字 | Low | Mid | Middle | Fixed | Xi,Jie | Lu,Guangwei | Wu, Fan | 2015-01-15
发起投票:投票之后，返回投票页面，投票状态没有变为已投票 | Low | High | High | Open | Xi,Jie | Jin,Liang | Wu, Fan | 2015-01-15 | 接口问题
点赞¦点击头像¦进入详情:事件冒泡处理 | Low | Middle | Middle | Fixed | Xi,Jie | Hu,Dandan | Wu, Fan | 2015-01-15
活动集锦点赞:点赞最后一个人名后面有顿号 | Low | Low | Low | Fixed | Xi,Jie | Zhang,Huaifei | Wu, Fan | 2015-01-15
有的投票选项没有内容,点击发起投票,出现错误提示,但是发起投票可以成功提交，并显示成功发送提示 | Low | Low | Low | Fixed | Xi,Jie | Lu,Guangwei | Wu, Fan | 2015-01-15
选择图片显示超出范围 | Low | Low | Low | Fixed | Xi,Jie | Lu, Guangwei | Wu, Fan | 2016-01-15
发现页面:不能评论 | Low | High | High | Fixed | Xi,Jie | Lu, Guangwei | Wu, Fan | 2016-01-15
发现页面:从广场页面和我的页面时,点击发现页面,发现页面不显示动态 | Low | Middle | Middle | Fixed | Xi,Jie | Lu, Guangwei | Wu, Fan | 2016-01-15
活动集锦签到:"更多"-"收起"失效 | Low | High | High | Fixed | Xi,Jie | Zhang, Huaifei | Wu, Fan | 2016-01-15
活动定位:点击定位查看活动地址（Tsidi 12F），地图不能打开 | Low | Low | Low | Open | Xi,Jie | Jin,Liang | Wu, Fan | 2016-01-18 | 后台需要传入数据
活动集锦:发布新的活动之后,页面不显示活动 | Low | Middle | Middle | Fixed | Xi,Jie | Lu,Guangwei | Wu, Fan | 2016-01-18
项目案例页面:点赞-不能被点赞或者点赞出现负数 | Low | High | High | Fixed | Xi,Jie | Hu,Dandan | Wu, Fan | 2016-01-18
项目案例及项目详情页面点赞:部分项目在项目案例页面的点赞数目与其项目详情页面的点赞数不同（例2015年的永辉项目） | Low | Middle | Middle | Fixed | Xi,Jie | Hu,Dandan | Wu, Fan | 2016-01-18
项目案例及项目详情页面点赞 - 在项目详情页面点赞后，点击项目案例进入项目案例页面，该页面点赞数不能随之变化 | Low | Middle | Middle | Fixed | Xi,Jie | Hu,Dandan | Wu, Fan | 2016-01-18
项目详情页 - 在图片右下角出现“灰色圆张”（例2015年 Motorola Mobility Inc） | Low | Low | Low | Fixed | Xi,Jie | Hu,Dandan | Wu, Fan | 2016-01-18
项目案例: 16年的项目数据没有 | Low | Low | Low | Open | Xi,Jie | Jin,Liang | Wu, Fan | 2016-01-18
dLife TV:时钟转移至右上角 | High | High | High | Fixed | Xi,Jie | Jin,Liang | Xi,Jie | 2016-01-19
dLife TV:左上角文字部分 | High | High | High | Fixed | Xi,Jie | Jin,Liang | Xi,Jie | 2016-01-19
dLife TV:团队成员显示. UIUX已移至第一栏 | High | High | High | Fixed | Xi,Jie | Jin,Liang | Xi,Jie | 2016-01-19
dLife TV:活动日历Touch事件,可以选择年份 | High | High | High | Fixed | Xi,Jie | Chen,LiHui | Xi,Jie | 2016-01-19
dLife TV:项目展示,安利项目增加封面图 | High | High | High | Fixed | Xi,Jie |  | Xi,Jie | 2016-01-19
dLife TV:导航栏增加嵌入式按钮,跳转[沙盘]和[dLife] | Middle | Middle | Middle | Open | Xi,Jie | Xi,Jie | Xi,Jie | 2016-01-19
发现状态发布，上传图片的bug | Low | High | High | Fixed | Xi,Jie | Zhang, Huaifei | Wu, Fan | 2016-01-19
发起投票页面，选择和日期显示异常 | Low | Low | Low | Fixed | Xi,jie | Zhang, Huaifei | Wu, Fan | 2016-01-15
发起投票界面选择图片异常 | Low | Low | Low | Fixed | Xi,Jie | Zhang, Huaifei | Wu, Fan | 2016-01-18

## To Do
To Do
User Story | Status | Case Owner | Assign To | Assign Date | Comments
团队风采页面(设计) | Planned | Xi,jie | N/A | 2016-01-14
部分项目图片读取太慢，图片显示不出来（例2013年的项目案例） | Planned | Xi,Jie | Hu,Dandan | 2016-01-18 | 性能优化问题
活动集锦:回复框,光标在回复提示的前面 | Planned | Xi,Jie | Lu,Guangwei | 2016-01-18 | 用户体验
活动集锦:点击更多>>,会出现收起，没有"<<" | Planned | Xi,Jie | Lu,Guangwei | 2016-01-18 | 用户体验
进入发现页面, 提示收到红包, 点击红包可以领取积分 | Planned | Xi,jie | N/A | 2016-01-21 | 新增功能

## TimeList
Timing List Tracking
Date Range | User Story | Asignee | Progress | Asign Date | Comments