## 工作表1
Sprint No. | App Name | ID No. | Backlog | User Story | Task | Asignee | Hour | Progress | Description
Sprint 10 | Inspection Lot | INSP-PO | PO - Functional Documentation | [Onshore] - Requirement | Business Analysis |  |  | 100%
[5 empty] | Get Mockup |  |  | 100%
[5 empty] | Discuss Requirements |  |  | 100%
[5 empty] | Confirm Requirements |  |  | 100%
|  |  |  | [Offshore] - Requirement | Define Backlogs |  |  | 100%
[5 empty] | Define Priority |  |  | 100%
[5 empty] | Generate documentation |  |  | 100%
|  |  |  | [Week 0] - Planning | Scrum Planning Meeting |  |  | 100%
|  |  |  | [Week 1] - FAQ | Requirement Support |  |  | 100%
[5 empty] | Backend Support |  |  | 60%
[5 empty] | Frontend Support |  |  | 60%
|  |  |  | [Week 1 - 2] - Testing | [Week 1] Testing Plan |  |  | 0%
[5 empty] | [Week 1] Testing Cases |  |  | 0%
[5 empty] | [Week 1] Testing Plan Review with SAP |  |  | 0%
[5 empty] | [Week 2] Testing Reuslt Documentation |  |  | 0%
|  |  |  | [Week 2] - Review | Preparing Final Review Data |  |  | 30%
[5 empty] | Final Review Documentation |  |  | 30%
[5 empty] | Final Review with SAP |  |  | 30%
| Inspection Lot | INSP-015 | Header Adjustment | [Backend Team] - Review | Backend Review |  |  | 0%
[5 empty] | Confirm Requirement |  |  | 0%
[5 empty] | Investigation |  |  | 0%
|  |  |  | [Model A] - Implementation | Header - Create Interface |  |  | 0%
[5 empty] | Header - Generate Functionality |  |  | 0%
[5 empty] | Header - Code Implement |  |  | 0%
[5 empty] | Header - Generate Data |  |  | 0%
[5 empty] | Header - Unit Testing |  |  | 0%
[5 empty] | Header - Code Review |  |  | 0%
[5 empty] | Header - Commit Implementation |  |  | 0%
|  |  |  | [Model B] - Implementation | Component - Create Interface |  |  | 0%
[5 empty] | Component - Generate Functionality |  |  | 0%
[5 empty] | Component - Code Implement |  |  | 0%
[5 empty] | Component - Generate Data |  |  | 0%
[5 empty] | Component - Unit Testing |  |  | 0%
[5 empty] | Component - Code Review |  |  | 0%
[5 empty] | Component - Commit Implementation |  |  | 0%
|  |  |  | [Model C] - Implementation | Footer - Create Interface |  |  | 0%
[5 empty] | Footer - Generate Functionality |  |  | 0%
[5 empty] | Footer - Code Implement |  |  | 0%
[5 empty] | Footer - Generate Data |  |  | 0%
[5 empty] | Footer - Unit Testing |  |  | 0%
[5 empty] | Footer - Code Review |  |  | 0%
[5 empty] | Footer - Commit Implementation |  |  | 0%
|  |  |  | [Frontend Team] - Review | Front Review |  |  | 0%
[5 empty] | Confirm Requirement |  |  | 0%
[5 empty] | Investigation |  |  | 0%
|  |  |  | [Model A] - Implementation | Header - Columns Define |  |  | 0%
[5 empty] | Header - Column A Implement |  |  | 0%
[5 empty] | Header - Column B Implement |  |  | 0%
[5 empty] | Header - Column C Implement |  |  | 0%
[5 empty] | Header - Column D Implement |  |  | 0%
[5 empty] | Header - Column E Implement |  |  | 0%
[5 empty] | Header - Code Review & Commit |  |  | 0%
|  |  |  | [Model B] - Implementation | Tab - Columns Define |  |  | 0%
[5 empty] | Tab - Column A Implement |  |  | 0%
[5 empty] | Tab - Column B Implement |  |  | 0%
[5 empty] | Tab - Column C Implement |  |  | 0%
[5 empty] | Tab - Column D Implement |  |  | 0%
[5 empty] | Tab - Column E Implement |  |  | 0%
[5 empty] | Tab - Code Review & Commit |  |  | 0%
|  |  |  | [Model C] - Implementation | Footer - Create Interface |  |  | 0%
[5 empty] | Footer - Generate Functionality |  |  | 0%
[5 empty] | Footer - Code Implement |  |  | 0%
[5 empty] | Footer - Generate Data |  |  | 0%
[5 empty] | Footer - Unit Testing |  |  | 0%
[5 empty] | Footer - Code Review |  |  | 0%
[5 empty] | Footer - Commit Implementation |  |  | 0%