## AM
Client | Project | PM | Win Probability 1 | Win Probability 2 | Personnel Number | Name | Email | Location | Skill | Role | Level | Status | Roll On | Roll Off | Plan Start Date | Plan End Date | Time(%) | Lead | From | Comments
Accenture - CIO | CIO003_Micro Experience | chengwu.wang | Sold | Sold | 11138014 | Song,Daoling | daoling.a.song@accenture.com | Shanghai | Ionic/AngularJS | Junior Developer | 11 | Hardlock | 2014-11-05 | 2016-08-31 |  |  | 100% | danny.x.wang | AM
|  |  |  | Sold | 10882423 | Zhang,Jipeng | jipeng.zhang@accenture.com | Dalian | Ionic/AngularJS | Junior Developer | 11 | Hardlock | 2013-08-19 | 2016-01-31 |  |  | 100% | danny.x.wang | AM
|  |  |  | Sold | 10884347 | Li,Xinhua | xinhua.li@accenture.com | Dalian | Ionic/AngularJS | Junior Developer | 11 | Hardlock | 2013-07-08 | 2016-08-31 |  |  | 100% | danny.x.wang | AM
|  |  |  | Sold | 11004839 | Fang,Ella Chao | c.fang@accenture.com | Shanghai | Ionic/AngularJS | Junior Developer | 12 | Hardlock | 2015-09-11 | 2016-08-31 |  |  | 100% | danny.x.wang | AM
|  |  |  | Sold | 11091462 | Antoine,Ory-lamballe | antoine.ory-lamballe@accenture.com | Shanghai | .Net | Senior Developer | 9 | Hardlock | 2015-04-24 | 2016-08-31 |  |  | 100% | danny.x.wang | AM
|  |  |  | Sold | 11042729 | Zhang,Arjun Jun | jun.d.zhang@accenture.com | Shanghai | Ionic/AngularJS | Senior Developer | 9 | Hardlock | 2014-11-17 | 2016-08-31 |  |  | 100% | danny.x.wang | AM
|  |  |  | Sold | 11186105 | Cai,Suzy Shuzhen | shuzhen.cai@accenture.com | Shanghai | Ionic/AngularJS | Senior Developer | 10 | Hardlock | 2015-10-19 | 2016-08-31 |  |  | 100% | danny.x.wang | AM
| CIO003_MyLearning | chengwu.wang | Sold | Sold | 10726872 | Li,Tianpeng | tianpeng.a.li@accenture.com | Dalian | Ionic/AngularJS | Senior Developer | 10 | Hardlock | 2015-04-06 | 2016-08-31 |  |  | 100% | danny.x.wang | AM
| CIO003_ISA Mobile App | chengwu.wang | Sold | Sold | 10726769 | Fei,Fiona Qiuping | fiona.qiuping.fei@accenture.com | Dalian | Ionic/AngularJS | Senior Developer | 10 | Hardlock | 2015-05-11 | 2016-08-31 |  |  | 100% | danny.x.wang | AM
|  |  |  | Sold | 10773109 | Wang,Zhaoqiang | zhaoqiang.wang@accenture.com | Dalian | Ionic/AngularJS | Senior Developer | 8 | Hardlock | 2015-05-11 | 2016-08-31 |  |  | 100% | danny.x.wang | AM
|  |  |  | Sold | 10755880 | An,Dapeng | dapeng.an@accenture.com | Dalian | Ionic/AngularJS | Senior Developer | 10 | Hardlock | 2015-05-11 | 2016-08-31 |  |  | 100% | danny.x.wang | AM
|  |  |  | Sold | 10773854 | Li,Li | li.d.li@accenture.com | Dalian | Ionic/AngularJS | Senior Developer | 9 | Hardlock | 2012-10-22 | 2016-02-29 |  |  | 100% | danny.x.wang | AM
| Design Studio UI Control Asset Project | chengwu.wang | Sold | Sold | 10254075 | Liu,Bo | bob.bo.liu@accenture.com | Dalian | Ionic/AngularJS | Senior Developer | 8 | Hardlock | 2015-03-01 | 2016-08-31 |  |  | 100% | danny.x.wang | AM
|  |  |  | Sold | 10772003 | Yu,David Bingjian | david.bingjian.yu@accenture.com | Dalian | Ionic/AngularJS | Senior Developer | 9 | Hardlock | 2015-05-11 | 2016-08-31 |  |  | 100% | danny.x.wang | AM
|  |  |  | Sold | 10777262 | Sun,Rongbo | rongbo.sun@accenture.com | Dalian | Ionic/AngularJS | Senior Developer | 10 | Hardlock | 2015-09-01 | 2016-08-31 |  |  | 100% | danny.x.wang | AM
|  |  |  | Sold | 11002342 | Zhang,Yaqi | yaqi.b.zhang@accenture.com | Dalian | Ionic/AngularJS | Junior Developer | 12 | Hardlock | 2014-08-19 | 2016-02-29 |  |  | 100% | danny.x.wang | AM
|  |  |  | Sold | 11005637 | Liu,Louis ZhuangZhuang | zhuangzhuang.a.liu@accenture.com | Dalian | Ionic/AngularJS | Junior Developer | 12 | Hardlock | 2014-09-29 | 2016-02-29 |  |  | 100% | danny.x.wang | AM
Accenture - CIO | Demands | chengwu.wang | Sold | Sold | Candidate1 |  |  | Shanghai | Ionic/AngularJS |  | SE-AM | [5 empty] | 100% | danny.x.wang | overdue Q4 1/1/2016
|  |  |  | Sold | Candidate2 |  |  | Shanghai | Ionic/AngularJS |  | SE-AM | [5 empty] | 100% | danny.x.wang | overdue Q4 1/1/2016
|  |  |  | Sold | Candidate3 |  |  | Shanghai | Ionic/AngularJS |  | SE-AM | [5 empty] | 100% | danny.x.wang | overdue Q4 1/1/2016
|  |  |  | Sold | Candidate4 |  |  | Shanghai | Ionic/AngularJS |  | SE-AM | [5 empty] | 100% | danny.x.wang | overdue Q4 1/1/2016
|  |  |  | Sold | Candidate5 |  |  | Shanghai | Ionic/AngularJS |  | SE-AM | [5 empty] | 100% | danny.x.wang | overdue Q4 1/1/2016
Accenture - CIO | CCA | chengwu.wang | Sold | Sold | 10972309 | He,Henry Qing | qing.he@accenture.com | Dalian | Ionic/AngularJS/.net | Senior Developer | 8 | Hardlock | 2015-03-01 | 2016-08-31 |  |  | 100% | danny.x.wang | AM | .Net
| SC | chengwu.wang | Sold | Sold | 10767522 | Gao,Jian | jian.a.gao@accenture.com | Dalian | Ionic/AngularJS/.net | Senior Developer | 10 | Hardlock | 2015-06-01 | 2016-08-31 |  |  | 100% | danny.x.wang | AM | .Net
Internal | BPO UC Gift | Jiong.wu | 90% | 90% | 11153428 | Liu,Xinyi | xinyi.liu@accenture.com | Dalian | Ionic/AngularJS/Js | Senior Developer | 10 | Hardlock | 2015-11-16 | 2016-01-15 |  |  | 100% | jiong.wu | AI
|  |  |  | 90% | 11148147 | Zhang,Wei | wei.g.zhang@accenture.com | Dalian | Ionic/AngularJS/.Net | Senior Developer | 9 | Hardlock | 2015-11-16 | 2016-01-15 |  |  | 100% | jiong.wu | AI
|  |  |  | 90% | 10665573 | Shao,Qiang | qiang.shao@accenture.com | Dalian | Ionic/.Net | Senior Developer | 9 | Hardlock | 2015-11-16 | 2016-01-15 |  |  | 100% | danny.x.wang | AM | Fill the java TA
|  |  |  | 90% | 10775057 | Li,Andy Jun | jun.h.li@accenture.com | Dalian | .Net | Senior Developer | 10 | Hardlock | 2015-11-16 | 2016-01-15 |  |  | 100% | danny.x.wang | AM | Fill java Developer
|  |  |  | 90% | 11166672 | Gai,Gavin Jiachuan | jiachuan.gai@accenture.com | Guangzhou | Designer | Designer | 11 | Hardlock | 2015-11-16 | 2016-01-16 |  |  | 100% | jiong.wu | AM
HK MTR | MTR ePMS | xiaoyu.wu | Sold | Sold | 11122068 | Shen,Jiang | jiang.shen@accenture.com | Guangzhou | Worklight/JQuery | Senior Developer | 10 | Hardlock | 2015-10-12 | 2015-12-04 |  |  | 100% | jinxin.wu | AM
|  |  |  | Sold | 11153920 | Zhao,Yang | yang.e.zhao@accenture.com | Guangzhou | Worklight/JQuery | Junior Developer | 12 | OJT |  |  | 2015-10-26 | 2015-12-04 | 100% | jinxin.wu | AM | Not in Digital,OJT OnProject
|  |  |  | Sold | 11148673 | Zheng,Yu | yu.a.zheng@accenture.com | Guangzhou | Worklight/JQuery | Junior Developer | 12 | OJT |  |  | 2015-10-26 | 2015-12-04 | 100% | jinxin.wu | AM | Not in Digital,OJT OnProject
|  |  |  | Sold | 10581555 | Xue,Yongzhang | yongzhang.xue@accenture.com | Guangzhou | Ionic/AngularJS | Scrum Master | 8 | Hardlock | 2015-08-01 | 2015-12-31 |  |  | 50% | jinxin.wu | AM
|  |  |  | Sold | 11148159 | Gong,Zhenjian | zhenjian.gong@accenture.com | Guangzhou | Ionic/AngularJS | Junior Developer | 12 | OJT |  |  | 2015-10-19 | 2015-11-30 | 100% | jinxin.wu | AM | Not in Digital
HK MTR | Elements Mall App PoC | jinxin.wu | 50% | 50% | 11138115 | Liang,Emily Minyu | minyu.liang@accenture.com | Guangzhou | Ionic/AngularJS | Junior Developer | 11 | OJT |  |  | 2015-10-19 | 2015-11-30 | 100% | jinxin.wu | AM | in Digital list
|  |  |  | 50% | 11121810 | Yang,Shengmeng | shengmeng.yang@accenture.com | Guangzhou | Ionic/AngularJS | Team Leader | 9 | OJT |  |  | 2015-10-19 | 2015-11-30 | 100% | jinxin.wu | AM | in Digital list
|  |  |  | 50% | 11153441 | Chen,Yanbing | yanbing.chen@accenture.com | Guangzhou | Ionic/AngularJS | Junior Developer | 12 | OJT |  |  | 2015-10-19 | 2015-11-30 | 100% | jinxin.wu | AM | Not in Digital
|  |  |  | 50% | 11148169 | He,Wason Weishun | weishun.he@accenture.com | Guangzhou | Ionic/AngularJS | Junior Developer | 12 | OJT |  |  | 2015-10-19 | 2015-11-30 | 100% | jinxin.wu | AM | Not in Digital
|  |  |  | 90% | 11116178 | Zeng,Mubin | mubin.zeng@accenture.com | Guangzhou | Photoshop, AxurePro | Designer | 10 | Future Hardlock | 2015-11-30 | 2016-08-31 |  |  | 100% | jinxin.wu | AI
|  |  |  | 90% | 11118653 | Liu,Jie | jie.c.liu@accenture.com | Guangzhou | Photoshop, AxurePro | Designer | 11 | Future Hardlock | 2015-11-30 | 2016-08-31 |  |  | 100% | jinxin.wu | AI
|  |  |  | 90% | 11122066 | Liu,Krystal Jiaxin | jiaxin.liu@accenture.com | Guangzhou | Photoshop, AxurePro | Designer | 11 | Future Hardlock | 2015-11-30 | 2016-08-31 |  |  | 100% | jinxin.wu | AI
|  |  |  | 90% | 11117026 | Cai,Fan | fan.cai@accenture.com | Guangzhou | Photoshop, AxurePro | Designer | 11 | Future Hardlock | 2015-11-30 | 2016-08-31 |  |  | 100% | jinxin.wu | AI
|  |  |  | 90% | 11138934 | He,Nico Zhengli | zhengli.he@accenture.com | Guangzhou | Photoshop, AxurePro | Designer | 11 | Future Hardlock | 2015-11-30 | 2016-08-31 |  |  | 100% | jinxin.wu | AI
|  |  |  | 90% | 11166672 | Gai,Gavin Jiachuan | jiachuan.gai@accenture.com | Guangzhou | Photoshop, AxurePro | Designer | 11 | Future Hardlock | 2015-11-30 | 2016-08-31 |  |  | 100% | jinxin.wu | AI | Not in Digital
|  |  |  | 90% | 11159095 | Chen,Johnny Zhaoqiang | zhaoqiang.chen@accenture.com | Guangzhou | Photoshop, AxurePro | Designer | 11 | Future Hardlock | 2015-11-30 | 2016-08-31 |  |  | 100% | jinxin.wu | AI
|  |  |  | 90% | Candidate3 |  |  | Guangzhou | Ionic/AngularJS | Senior Developer | 10 | Future Hardlock | 2015-11-30 | 2016-08-31 |  |  | 100% | jinxin.wu | AI
|  |  |  | 90% | Candidate4 |  |  | Guangzhou | Ionic/AngularJS | Senior Developer | 10 | Future Hardlock | 2015-11-30 | 2016-08-31 |  |  | 100% | jinxin.wu | AI
|  |  |  | 90% | Candidate5 |  |  | Guangzhou | Ionic/AngularJS | Senior Developer | 10 | Future Hardlock | 2015-11-30 | 2016-08-31 |  |  | 100% | jinxin.wu | AI
|  |  |  | 90% | Candidate6 |  |  | Guangzhou | Ionic/AngularJS | Senior Developer | 10 | Future Hardlock | 2015-11-30 | 2016-08-31 |  |  | 100% | jinxin.wu | AI
|  |  |  | 90% | Candidate7 |  |  | Guangzhou | Ionic/AngularJS | Junior Developer | 11 | Future Hardlock | 2015-11-30 | 2016-08-31 |  |  | 100% | jinxin.wu | AI
China National Offshore Oil Corporation | Cnooc MADP | jinxin.wu | 30% | 30% | Candidate1 |  |  | Beijing | Worklight | Technical Architect | 8 |  | 2016-01-02 | 2016-03-31 |  |  | 100% | jinxin.wu | AM
|  |  |  | 80% | 11104442 | Guo,Day Yuhui | yuhui.guo@accenture.com | Guangzhou | Js | Senior Developer | 10 | Hardlock | 2015-11-23 | 2016-02-12 |  |  | 100% | jinxin.wu | AI
|  |  |  | 80% | 11104443 | Zhao,Chunsen | chunsen.zhao@accenture.com | Guangzhou | Js | Senior Developer | 11 | Hardlock | 2015-11-23 | 2016-02-12 |  |  | 100% | jinxin.wu | AI
AliBaba | Shell IOT | danny.x.wang | 50% | 50% | Candidate1 |  |  | Shanghai/Dalian/GZ | Ionic | Developer | SSE/TL |  | 2015-12-25 | 2016-12-25 |  |  | 100% | danny.x.wang | AM | Not Sure how much FTE
|  |  |  | 50% | Candidate2 |  |  | Shanghai/Dalian/GZ | Ionic | Developer | SSE/TL |  | 2015-12-25 | 2016-12-26 |  |  | 100% | danny.x.wang | AM
Internal | Digital AM Asset | danny.x.wang | 80% | 80% | Candidate1 |  |  | Dalian/Shanghai | Ionic/AngularJS | Developer | TL/AM |  | 2015-12-31 | 2016-08-31 |  |  | 100% | danny.x.wang | AM | 3 front end developers, TL/AM
|  |  |  | 80% | Candidate2 |  |  | Dalian/Shanghai | Ionic/AngularJS | Developer | TL/AM |  | 2015-12-31 | 2016-08-31 |  |  | 100% | danny.x.wang | AM
|  |  |  | 80% | Candidate3 |  |  | Dalian/Shanghai | Ionic/AngularJS | Developer | TL/AM |  | 2015-12-31 | 2016-08-31 |  |  | 100% | danny.x.wang | AM
|  |  |  | 80% | Candidate4 |  |  | Dalian/Shanghai | Ionic/AngularJS | Developer | SSE/TL |  | 2015-12-31 | 2016-08-31 |  |  | 100% | danny.x.wang | AM | 3 front end developers, SSE/TL
|  |  |  | 80% | Candidate5 |  |  | Dalian/Shanghai | Ionic/AngularJS | Developer | SSE/TL |  | 2015-12-31 | 2016-08-31 |  |  | 100% | danny.x.wang | AM
|  |  |  | 80% | Candidate6 |  |  | Dalian/Shanghai | Ionic/AngularJS | Developer | SSE/TL |  | 2015-12-31 | 2016-08-31 |  |  | 100% | danny.x.wang | AM
|  |  |  | 80% | Candidate7 |  |  | Dalian/Shanghai/GZ | Ionic/AngularJS | Developer | SSE/TL |  | 2016-01-31 | 2016-08-31 |  |  | 100% | danny.x.wang | AM
|  |  |  | 80% | Candidate8 |  |  | Dalian/Shanghai/GZ | Ionic/AngularJS | Developer | SSE/TL |  | 2016-01-31 | 2016-08-31 |  |  | 100% | danny.x.wang | AM
|  |  |  | 80% | Candidate9 |  |  | Dalian/Shanghai/GZ | Ionic/AngularJS | Developer | SSE/TL |  | 2016-01-31 | 2016-08-31 |  |  | 100% | danny.x.wang | AM
|  |  |  | 80% | Candidate10 |  |  | Dalian/Shanghai/GZ | Ionic/AngularJS | Developer | SSE/TL |  | 2016-01-31 | 2016-08-31 |  |  | 100% | danny.x.wang | AM
|  |  |  | 80% | Candidate11 |  |  | Dalian/Shanghai/GZ | Ionic/AngularJS | Developer | SSE/TL |  | 2016-01-31 | 2016-08-31 |  |  | 100% | danny.x.wang | AM
SMB(Japan) | SMB | hongbin.niu | 95% | 95% | 11165379 | Du,Tony Wenbin | wenbin.du@accenture.com | Dalian | Js/AngularJs | Leader | TL |  | 2015-12-15 | 2016-03-31 |  | 2015-12-30 | 100% | zheng.yan | AM | in AI of Digital
|  |  |  | 95% | 11161760 | Li,Gavin Zhichao | zhichao.li@accenture.com | Dalian | Js/AngularJs | Senior Developer | SSE |  | 2015-12-15 | 2016-03-31 |  | 2015-12-30 | 100% | zheng.yan | AM | in AI of Digital
|  |  |  | 95% | 11160071 | Wu,Carl Baofeng | baofeng.wu@accenture.com | Dalian | Js | Senior Developer | SSE |  | 2015-12-15 | 2016-03-31 |  | 2015-11-30 | 100% | zheng.yan | AM | in AI of Digital
|  |  |  | 95% | 11160972 | Zhang,Sailor Xiangnan | xiangnan.zhang@accenture.com | Dalian | Js | Senior Developer | SSE |  | 2015-12-15 | 2016-03-31 |  | 2015-12-14 | 100% | zheng.yan | AM | in AI of Digital
|  |  |  | 95% | 11087478 | Li,Linchun | linchun.li@accenture.com | Dalian | Js | Developer | SSE |  | 2015-12-15 | 2016-03-31 |  |  | 100% | zheng.yan | AM | in AI of Digital
|  |  |  | 95% | 11161763 | Jiao,Wenzhi | wenzhi.jiao@accenture.com | Dalian | Js/AngularJs | Developer | SE |  | 2016-01-01 | 2016-03-31 |  | 2015-12-30 | 100% | zheng.yan | AM | in AI of Digital
|  |  |  | 95% | Candidate1 |  |  | DL/SH | Ionic/AngularJS | Developer | SE |  | 2016-01-01 | 2016-03-31 |  |  | 100% | zheng.yan | AM
|  |  |  | 95% | Candidate2 |  |  | DL/SH | Ionic/AngularJS | Tester | SSE |  | 2016-01-01 | 2016-03-31 |  |  | 100% | zheng.yan | AM
|  |  |  | 95% | Candidate3 |  |  | DL/SH | Ionic/AngularJS | Tester | SSE |  | 2016-01-01 | 2016-03-31 |  |  | 100% | zheng.yan | AM
|  |  |  | 95% | Candidate4 |  |  | DL/SH | Ionic/AngularJS | Tester | SE |  | 2016-02-01 | 2016-03-31 |  |  | 100% | zheng.yan | AM
|  |  |  | 95% | Candidate5 |  |  | DL/SH | Ionic/AngularJS | Tester | SE |  | 2016-02-01 | 2016-03-31 |  |  | 100% | zheng.yan | AM
|  |  |  | 95% | Candidate6 |  |  | DL/SH | Ionic/AngularJS | Tester | SE |  | 2016-03-01 | 2016-03-31 |  |  | 100% | zheng.yan | AM
|  |  |  | 70% | 11116180 | Ou,Lijie | lijie.ou@accenture.com | Guangzhou | Photoshop, AxurePro | Designer | 11 | Proposed | 2015-12-07 | 2016-01-29 |  |  | 100% | danny.x.wang | AM
|  |  |  | 70% | 11183596 | Yu,Josh Peng | p.yu@accenture.com | Dalian | Js/AngularJs | Senior Developer | 10 | Hardlock | 2015-12-07 | 2016-01-29 |  |  | 100% | danny.x.wang | AM
Mead Johnson | IOS App upgrade | kevin.kui.yang | 50% | 50% | Candidate1 |  |  | Guangzhou | IOS | IOS Developer Leader | 7 | Proposed |  |  | 2015-12-14 | 2016-05-13 | 100% | jinxin.wu | AM
|  |  |  | 50% | 11121810 | Yang,Shengmeng | shengmeng.yang@accenture.com | Guangzhou | IOS | Senior iOS Developer | 9 | Proposed |  |  | 2015-12-14 | 2016-06-03 | 100% | jinxin.wu | AM
|  |  |  | 50% | 11138115 | Liang,Emily Minyu | minyu.liang@accenture.com | Guangzhou | IOS | IOS Developer | 10 | Proposed |  |  | 2015-12-28 | 2016-04-15 | 100% | jinxin.wu | AM
|  |  |  | 50% | 11116178 | Zeng,Mubin | mubin.zeng@accenture.com | Guangzhou |  | Designer | 9 | Proposed |  |  | 2015-12-14 | 2016-01-15 | 100% | jinxin.wu | AM
Shenzhen Gas | Prepare of Project | Jiong.wu |  |  | 11153428 | Liu,Xinyi | xinyi.liu@accenture.com | Dalian | Ionic/AngularJS/Js | Senior Developer | 10
[5 empty] | 11148147 | Zhang,Wei | wei.g.zhang@accenture.com | Dalian | Ionic/AngularJS/.Net | Senior Developer | 9
Shenzhen Gas | BI Project | koi.hu | 50% | 50% | 11118653 | Liu,Jie | jie.c.liu@accenture.com | Shenzhen | Designer | Designer | 11 | Proposed |  |  | 2015-12-14 | 2016-03-31 | 100% | jinxin.wu | AM
|  |  |  | 50% | Candidate1 |  |  | Shenzhen |  | Developer |  |  |  |  | 2015-11-23 | 2015-11-23 |  | jinxin.wu | AM | One day
|  |  |  | 50% | Candidate2 |  |  | Shenzhen |  | Designer |  |  |  |  | 2015-11-23 | 2015-11-27 |  | jinxin.wu | AM | One week
Shenzhen Gas | Shenzhen Gas Cell A | danny.x.wang | 50% | 50% | Candidate1 |  |  | Guangzhou | Ionic/AngularJS | IOS Developer | SE-TL | Proposed |  |  | 2015-01-04 |  | 100% | jinxin.wu | AM | Jan or March for mobile
|  |  |  | 50% | Candidate2 |  |  | Guangzhou | Ionic/AngularJS | IOS Developer | SE-TL | Proposed |  |  | 2015-01-04 |  | 100% | jinxin.wu | AM | Jan or March for mobile
|  |  |  | 50% | Candidate3 |  |  | Guangzhou | Ionic/AngularJS | IOS Developer | SE-TL | Proposed |  |  | 2015-01-04 |  | 100% | jinxin.wu | AM | Jan or March for mobile
Shenzhen Gas | Shenzhen Gas Cell B | danny.x.wang | 50% | 50% | Candidate1 |  |  | Guangzhou | Ionic/AngularJS | IOS Developer | SE-TL | Proposed |  |  | 2015-01-04 |  | 100% | jinxin.wu | AM | Jan or March for mobile
|  |  |  | 50% | Candidate2 |  |  | Guangzhou | Ionic/AngularJS | IOS Developer | SE-TL | Proposed |  |  | 2015-01-04 |  | 100% | jinxin.wu | AM | Jan or March for mobile
|  |  |  | 50% | Candidate3 |  |  | Guangzhou | Ionic/AngularJS | IOS Developer | SE-TL | Proposed |  |  | 2015-01-04 |  | 100% | jinxin.wu | AM | Jan or March for mobile
Shenzhen Gas | Shenzhen Gas Cell C | danny.x.wang | 50% | 50% | Candidate1 |  |  | Guangzhou | Ionic/AngularJS | IOS Developer | SE-TL | Proposed |  |  | 2015-01-04 |  | 100% | jinxin.wu | AM | Jan or March for mobile
|  |  |  | 50% | Candidate2 |  |  | Guangzhou | Ionic/AngularJS | IOS Developer | SE-TL | Proposed |  |  | 2015-01-04 |  | 100% | jinxin.wu | AM | Jan or March for mobile
|  |  |  | 50% | Candidate3 |  |  | Guangzhou | Ionic/AngularJS | IOS Developer | SE-TL | Proposed |  |  | 2015-01-04 |  | 100% | jinxin.wu | AM | Jan or March for mobile

## AI-Project
Client | Project | Name | Email | Location | Level | Personnel Number | State | Roll On | Roll Off | Comment
SAP | SAP Fiori | Sun, Minmin | minmin.sun@accenture.com | Shanghai | TL | 11036205 | Hardlock | 2015-09-03 | 2015-12-31
SAP | SAP Fiori | Ma, Kevin Lin | l.a.ma@accenture.com | Shanghai | SSE | 11125778 | Hardlock | 2015-07-13 | 2016-03-31
SAP | SAP Fiori | Qu, Ying | ying.qu@accenture.com | Shanghai | SSE | 11148632 | Hardlock | 2015-08-03 | 2016-03-31
SAP | SAP Fiori | Tang, Wendy Wenjing | wenjing.tang@accenture.com | Shanghai | SSE | 11090389 | Hardlock | 2016-01-04 | 2016-02-22
SAP | SAP Fiori | Qian, Rebecca Xuejiao | x.qian@accenture.com | Shanghai | SE | 11010639 | Hardlock | 2015-07-01 | 2016-03-31
SAP | SAP Fiori | Feng, Yao | yao.feng@accenture.com | Shanghai | SSE | 11163279 | Hardlock | 2015-07-01 | 2016-03-31
SAP | SAP Fiori | Deng, xueliang | xueliang.deng@accenture.com | Shanghai | SE | 11137695 | Hardlock | 2015-06-15 | 2016-03-31
SAP | SAP Fiori | Wang, Tracy Xiaonan | xiaonan.d.wang@accenture.com | Shanghai | SE | 11087910 | Hardlock | 2015-04-01 | 2016-03-31
SAP | SAP Fiori | huang, Hongxia | hongxia.huang@accenture.com | Shanghai | SSE | 11090063 | Hardlock | 2015-04-03 | 2016-04-01
SAP | SAP Fiori | Shi, Vikcy Hui | hui.shi@accenture.com | Shanghai | SSE | 11157486 | Hardlock | 1/0/2015 | 2016-03-31
SAP | SAP Fiori | Gu, Chenqing | chenqing.gu@accenture.com | Shanghai | ASE | 11145551 | Hardlock | 2015-12-16 | 2016-02-22
SAP | SAP Fiori | Ni, Fang | fang.ni@accenture.com | Shanghai | ASE | 11145562 | Hardlock | 2015-12-10 | 2016-02-22
iBank | iBank Execution Phase IT_SI | Wu, Baofeng | baofeng.wu@accenture.com | Dalian | SSE | 11160071 | Hardlock | 12-28-2015 | 6-31-2016
BMW | BMW CN.DIGITAL | Ying, Mingming | mingming.ying@accenture.com | Shanghai | SSE | 11100506 | Hardlock | 2015-08-17 | 2016-12-31
BMW | BMW CN.DIGITAL | Ping, Yunjie | yunjie.ping@accenture.com | Shanghai | ASE | 11145500 | Hardlock | 2015-09-01 | 2016-02-01
BMW | BMW CN.DIGITAL | Jiang, Ping | ping.jiang@accenture.com | Shanghai | ASE | 11148690 | Hardlock | 2015-09-01 | 2016-02-01
L’orealParis | L’orealParis | Zhu, Linda Xiaolin | xiaolin.zhu@accenture.com | Shanghai | SSE | 10876735 | Hardlock | 2015-12-04 | 2016-01-30
Accenture - CIO | CIO 003 - MMC | Liu, Xinyi | xinyi.liu@accenture.com | Dalian | SSE | 11153428 | Hardlock | 0 | 0
Accenture - CIO | CIO 003 - MMC | Zhang, Wei | wei.g.zhang@accenture.com | Dalian | TL | 11148147 | Hardlock | 0 | 0
Bristol-Myers Squibb | BMS Responsive Design | Sun, Tina Yanting | yanting.sun@accenture.com | Shanghai | TL | 10922391 | OJT | 0 | 2015-12-04
Bristol-Myers Squibb | CIO MMC | Kan, Jiangtao | jiangtao.kan@accenture.com | Shanghai | SE | 11165390 | Future Hardlock | 2015-12-15 | 2016-01-12
Bristol-Myers Squibb | BMS Responsive Design | Zhang, Miao | miao.c.zhang@accenture.com | Shanghai | SE | 11165391 | OJT | 0 | 0
Accenture - CIO | 0 | Hou, Ming | ming.hou@accenture.com | Shanghai | ASE | 11145563 | OJT | 2016-01-04 | 0
Accenture - CIO | 年会项目 | Hua, Shenglei | shenglei.hua@accenture.com | Shanghai | ASE | 11145560 | Future Hardlock | 2016-01-04 | 0
Accenture - CIO | MMC Team 3 (AEM Asset) | Dong, Tianwen | tianwen.dong@accenture.com | Shanghai | TL | 11199332 | Hardlock | 2015-12-01 | 2015-12-31
Accenture - CIO | MMC Team 4 & Team 5 | Du, Tony Wenbin | wenbin.du@accenture.com | Dalian | TL | 11165379 | 0 | 0 | 0
Accenture - AM | AM - Digr | Fu, William Yong | yong.fu@accenture.com | Shanghai | TL | 11082411 | OJT | 2015-12-21 | 2016-02-28
Accenture - CIO | MMC Team 4 & Team 5 | Fan, Yang | yang.fan@accenture.com | Shanghai | SE | 11140781 | Vacation | 0 | 0 | Confirm with chengwu, start middle of Feb.
Accenture - CIO | CIO 003 - MMC | Li, Linchun | linchun.li@accenture.com | Dalian | SSE | 11087478 | Future Hardlock | 1-18-2016 | 8-31-2016
Accenture - CIO | 年会项目 | Han, Mei | m.a.han@accenture.com | Shanghai | ASE | 11147836 | Hardlock | 2015-12-15 | 2016-01-12
Accenture - CIO | CIO - Asset | Zhou, Wang | wang.a.zhou@accenture.com | Shanghai | ASE | 11148693 | Future Hardlock | 0 | 0 | Confirm with chengwu.
Accenture - CIO | CIO - Asset | Hua, Chenxing | chenxing.hua@accenture.com | Shanghai | ASE | 11148683 | Future Hardlock | 0 | 0
Accenture - AM | AM - Digr | Liu, Liu | liu.a.liu@accenture.com | Shanghai | ASE | 11148696 | OJT | 2015-12-21 | 2016-02-28 | Confirm with chengwu.
Accenture - CIO | CIO 001 | Yu, Josh Peng | peng.yu@accenture.com | Dalian | SSE | 11183596 | Hardlock | 2015-12-14 | 2016-08-31
Accenture - CIO | CIO 001 | Zhang, Sailor Xiangnan | xiangnan.zhang@accenture.com | Dalian | SSE | 11160972 | Hardlock | 2015-12-21 | 2016-08-31
Accenture - CIO | CIO 001 | Li, Gavin Zhichao | zhichao.li@accenture.com | Dalian | SSE | 11161760 | Hardlock | 2015-12-21 | 2016-08-31
Accenture - AM | AM - Digr | Fu, William Yong | yong.fu@accenture.com | Shanghai | TL | 11082411 | OJT | 2015-12-21 | 2016-02-28 | Confirm with wujiong
Accenture - AM | AM - Digr | Mao, Allison Yunhui | yunhui.mao@accenture.com | Shanghai | SSE | 10993500 | OJT | 2015-12-21 | 2016-02-28
Accenture - AM | AM - Digr | Wang, Daisy Weihong | weihong.wang@accenture.com | Shanghai | SSE | 11009989 | OJT | 2015-12-21 | 2016-02-28
Accenture - AM | AM - Digr | Jiang, Xujing | xujing.jiang@accenture.com | Shanghai | SE | 11090383 | OJT | 2015-12-21 | 2016-02-28
Accenture - AM | AM - Digr | Dong, Jiawei | jiawei.dong@accenture.com | Shanghai | ASE | 11145555 | Hardlock | 2015-12-21 | 2016-02-28
#N/A | #N/A | Xiao, Jintao | jintao.xiao@accenture.com | Shanghai | ASE | 11145572 | Hardlock | 2015-12-28 | #N/A
Accenture - Digital | dLife | Hu, Dandan | dandan.hu@accenture.com | Shanghai | ASE | 11145564 | Hardlock | 0 | 0
Accenture - Digital | dLife | Zhang, Huaifei | huaifei.zhang@accenture.com | Shanghai | ASE | 11145582 | Hardlock | 0 | 0
Accenture - Digital | O2O | Huang, Yun | yun.huang@accenture.com | Shanghai | ASE | 11145561 | Hardlock | 0 | 0
Accenture - Digital | O2O | Wang, Kena | kena.wang@accenture.com | Shanghai | ASE | 11147835 | Hardlock | 0 | 0
0 | 0 | Zeng, Mubin | mubin.zeng@accenture.com | Guangzhou | TL | 11116180 | OJT | 0 | 0
兖矿集团 | 信息化建设与大数据整合项目 | He, Nico Zhengli | zhengli.he@accenture.com | Guangzhou | SE | 11138934 | Hardlock | 12-20-2015 | 1-15-2016
香港中华燃气 | Towngar | Liu, Jie | jie.c.liu@accenture.com | Guangzhou | SE | 11118653 | Hardlock | 12-21-2015 | 1-31-2016
Accenture - Digital | 年会项目 | Chen, Lihui | lihui.chen@accenture.com | Shanghai | ASE | 11145550 | Hardlock | 2015-12-15 | 2016-01-12
Unicharm | Unicharm | Gai, Gavin Jiachuan | jiachuan.gai@accenture.com | Guangzhou | SE | 11166672 | OJT | 0 | 0
0 | 0 | Cai, Fan | fan.cai@accenture.com | Guangzhou | SE | 11117026 | OJT | 0 | 0
0 | 0 | Ou, Lijie | lijie.ou@accenture.com | Guangzhou | SE | 11116180 | OJT | 0 | 0
0 | 0 | Liu, Krystal Jiaxin | jiaxin.liu@accenture.com | Guangzhou | SE | 11122066 | OJT | 0 | 0
0 | 0 | Chen, Johnny Zhaoqiang | zhaoqiang.chen@accenture.com | Guangzhou | SE | 11159095 | OJT | 0 | 0
0 | 0 | Guo, Yuhui | yuhui.guo@accenture.com | Guangzhou | SSE | 11104442 | OJT | 0 | 0
0 | 0 | Zhao, Chunsen | chunsen.zhao@accenture.com | Guangzhou | SSE | 11104443 | OJT | 0 | 0
0 | NTP | Lv, Dage | dage.lv@accenture.com | Dalian | TL | 11163253 | Hardlock | 1-4-2015 | 8-31-2016
0 | 0 | Zhou, Miao | miao.zhou@accenture.com | Shanghai | SE | 11090103 | OJT | 0 | 0
0 | 年会项目 | Hao, Junyu | junyu.hao@accenture.com | Shanghai | ASE | 11145559 | Hardlock | 2015-12-15 | 2016-01-12
Accenture - CIO | UI Design Studio Project | Wu, Hongjian | hongjian.wu@accenture.com | Shanghai | ASE | 11145569 | Hardlock | 2015-12-28 | 0 | Share Evan's code to them
0 | 0 | Lu, Guangwei | guangwei.lu@accenture.com | Shanghai | ASE | 11148689 | OJT | 0 | 0 | Share Evan's code to them
0 | CIO 001 | Jiao, Wenzhi | wenzhi.jiao@accenture.com | Dalian | SE | 11161763 | OJT | 0 | 0
0 | Janpanese Android | Jia, Yuzhuo | yuzhuo.jia@accenture.com | Dalian | ASE | 11154869 | Hardlock | 12-21-2015 | 8-31-2016
0 | 0 | Zhang, Yao | yao.b.zhang@accenture.com | Dalian | ASE | 11154886 | OJT | 0 | 0
0 | Janpanese Android | Liu, Danyu | danyu.liu@accenture.com | Dalian | ASE | 11154860 | Hardlock | 1-12-2016 | 3-31-2016
0 | 0 | Wang, Weiqi | weiqi.a.wang@accenture.com | Dalian | ASE | 11154869 | OJT | 0 | 0
0 | 0 | Zhang, Xuanwei | xuanwei.zhang@accenture.com | Dalian | ASE |  | 0 | 0 | 0
0 | 0 | Yang, Donghui | donghui.yang@accenture.com | Dalian | ASE | 11154852 | OJT | 0 | 0
0 | 0 | Lu, Jing | jing.a.lu@accenture.com | Shanghai | SE | 11090034 | Parent Leave | 0 | 0
Formulas:
Roll On = VLOOKUP([Name],'AI-Staff'!A2:Q71,11,FALSE)
Roll Off = VLOOKUP([Name],'AI-Staff'!A2:Q71,12,FALSE)

## AI-Staff
Name | Email | Level | Technical Skill | Design Skill | Term | Skill Description | Status | Project | Client | Roll On | Roll Off | Comments | Location | Personal Number | Contact Number | Responsible person
Sun, Minmin | minmin.sun@accenture.com | TL | Html5, JS |  |  |  | Hardlock | SAP Fiori | SAP | 2015-09-03 | 2015-12-31 |  | Shanghai | 11036205 | 18521516139 | Sun, Minmin
Ma, Kevin Lin | l.a.ma@accenture.com | SSE | Html5, JS |  |  |  | Hardlock | SAP Fiori | SAP | 2015-07-13 | 2016-03-31 |  | Shanghai | 11125778 |  | Sun, Minmin
Qu, Ying | ying.qu@accenture.com | SSE | Html5, JS |  |  |  | Hardlock | SAP Fiori | SAP | 2015-08-03 | 2016-03-31 |  | Shanghai | 11148632 | 15026952024 | Sun, Minmin
Tang, Wendy Wenjing | wenjing.tang@accenture.com | SSE | Html5, JS/AngularJS |  |  |  | Hardlock | SAP Fiori | SAP | 2016-01-04 | 2016-02-22 |  | Shanghai | 11090389 | 13262512492 | Tang, Wendy Wenjing
Qian, Rebecca Xuejiao | x.qian@accenture.com | SE | Html5, JS |  |  |  | Hardlock | SAP Fiori | SAP | 2015-07-01 | 2016-03-31 |  | Shanghai | 11010639
Feng, Yao | yao.feng@accenture.com | SSE | Html5, JS |  |  |  | Hardlock | SAP Fiori | SAP | 2015-07-01 | 2016-03-31 |  | Shanghai | 11163279 | 13023166420
Deng, xueliang | xueliang.deng@accenture.com | SE | Html5, JS |  |  |  | Hardlock | SAP Fiori | SAP | 2015-06-15 | 2016-03-31 |  | Shanghai | 11137695 | 18964095772
Wang, Tracy Xiaonan | xiaonan.d.wang@accenture.com | SE | Html5, JS |  |  |  | Hardlock | SAP Fiori | SAP | 2015-04-01 | 2016-03-31 |  | Shanghai | 11087910 | 13262698705 | Fu, William Yong
huang, Hongxia | hongxia.huang@accenture.com | SSE | Html5, JS |  |  |  | Hardlock | SAP Fiori | SAP | 2015-04-03 | 2016-04-01 |  | Shanghai | 11090063 | 15721169252
Shi, Vikcy Hui | hui.shi@accenture.com | SSE | Html5, JS |  |  |  | Hardlock | SAP Fiori | SAP | 1/0/2015 | 2016-03-31 |  | Shanghai | 11157486 | 18521064486
Gu, Chenqing | chenqing.gu@accenture.com | ASE | Html5, JS |  |  |  | Hardlock | SAP Fiori | SAP | 2015-12-16 | 2016-02-22 |  | Shanghai | 11145551 | 13585840249 | Zhu, Linda Xiaolin
Ni, Fang | fang.ni@accenture.com | ASE | Html5, JS |  |  |  | Hardlock | SAP Fiori | SAP | 2015-12-10 | 2016-02-22 |  | Shanghai | 11145562 | 15800672379 | Zhu, Linda Xiaolin
Ying, Mingming | mingming.ying@accenture.com | SSE | Html5, JS |  |  |  | Hardlock | BMW CN.DIGITAL | BMW | 2015-08-17 | 2016-12-31 |  | Shanghai | 11100506 | 18658422652 | Ying, Mingming
Ping, Yunjie | yunjie.ping@accenture.com | ASE | Html5, JS |  |  |  | Hardlock | BMW CN.DIGITAL | BMW | 2015-09-01 | 2016-02-01 |  | Shanghai | 11145500 |  | Ying, Mingming
Jiang, Ping | ping.jiang@accenture.com | ASE | Html5, JS |  |  |  | Hardlock | BMW CN.DIGITAL | BMW | 2015-09-01 | 2016-02-01 |  | Shanghai | 11148690 | 13162551909 | Ying, Mingming
Zhu, Linda Xiaolin | xiaolin.zhu@accenture.com | SSE | Html5 |  |  |  | Hardlock | L’orealParis | L’orealParis | 2015-12-04 | 2016-01-30 |  | Shanghai | 10876735 | 13817476149 | Zhu, Linda Xiaolin
Sun, Tina Yanting | yanting.sun@accenture.com | TL | Html5 | Photoshop, AxurePro | 5 | Expert in Photoshop, Illustrator & Axure, Familiar with Indesign. | OJT | BMS Responsive Design | Bristol-Myers Squibb |  | 2015-12-04 | Leave vacation from 24 Dec,2015 to 4 Jan,2016 | Shanghai | 10922391 | 13524105067 | Sun, Tina Yanting
Kan, Jiangtao | jiangtao.kan@accenture.com | SE |  | Photoshop, AxurePro | 3 | Familiar with Photoshop, Axure & Xcode, understand Illustrator, Flash. | Future Hardlock | CIO MMC | Bristol-Myers Squibb | 2015-12-15 | 2016-01-12 |  | Shanghai | 11165390 | 18689379998 | Sun, Tina Yanting
Zhang, Miao | miao.c.zhang@accenture.com | SE |  | Photoshop, AxurePro | 2 | Familiar with AxurePro, understand Photoshop, Illustrator, SPSS, Flash. | OJT | BMS Responsive Design | Bristol-Myers Squibb |  |  | Leave vacation from 28 Dec,2015 to 4 Jan,2016 | Shanghai | 11165391 | 15850560653 | Sun, Tina Yanting
Hou, Ming | ming.hou@accenture.com | ASE | Html5, JS |  |  |  | OJT |  | Accenture - CIO | 2016-01-04 |  | Leave vacation from 28 Dec,2015 to 4 Jan,2016 | Shanghai | 11145563 | 15800878231 | Zhu, Linda Xiaolin
Hua, Shenglei | shenglei.hua@accenture.com | ASE | Html5, JS |  |  |  | Future Hardlock | 年会项目 | Accenture - CIO | 2016-01-04 |  |  | Shanghai | 11145560 | 18616930779 | Zhu, Linda Xiaolin
Xiao, Jintao | jintao.xiao@accenture.com | ASE | Html5, JS |  |  | Familiar with JS/Angular & Html5, understand ionic & jQuery | Hardlock | 年会项目 | Accenture - CIO | 2015-12-28 |  |  | Shanghai | 11145572 | 18817378046 | Zhu, Linda Xiaolin
Wu, Hongjian | hongjian.wu@accenture.com | ASE | Html5, JS |  |  |  | Hardlock | UI Design Studio Project | Accenture - CIO | 2015-12-28 |  | Share Evan's code to them | Shanghai | 11145569 | 18018608024 | Zhu, Linda Xiaolin
Dong, Tianwen | tianwen.dong@accenture.com | TL | Html5, JS/AngularJS |  |  | 1.Front-end: Expert in JS & Html5, familiar with Angular JS 2.Back-end: Familiar with PHP, Java, Database | Hardlock | MMC Team 3 (AEM Asset) | Accenture - CIO | 2015-12-01 | 2015-12-31 |  | Shanghai | 11199332 | 15763191239 | Dong, Tianwen
Fan, Yang | yang.fan@accenture.com | SE | Html5 |  |  | Familiar with JS/Angular, Html5 | Vacation | MMC Team 4 & Team 5 | Accenture - CIO |  |  | Confirm with chengwu, start middle of Feb. Leave vacation from 28 Dec,2015 to 4 Jan,2016 (Dance) | Shanghai | 11140781 | 15077929354 | Tang, Wendy Wenjing
Han, Mei | m.a.han@accenture.com | ASE | Html5, JS | Photoshop |  | Familiar with Photoshop, understand Illustrator.(Familiar with Html5, understand JS/Jquery) | Hardlock | 年会项目 | Accenture - CIO | 2015-12-15 | 2016-01-12 |  | Shanghai | 11147836 | 13774477786 | Sun, Tina Yanting
Zhou, Wang | wang.a.zhou@accenture.com | ASE | Html5, JS |  |  | Familiar with Html5, understand JS/Jquery | Future Hardlock | CIO - Asset | Accenture - CIO |  |  | Confirm with chengwu. 假期-64hours | Shanghai | 11148693 | 13298355753 | Zhu, Linda Xiaolin
Fu, William Yong | yong.fu@accenture.com | TL | Html5, JS/AngularJS |  |  | 1. Front-end: Expert in JS/Angular JS and SAP HTML5. 2. Back-end: Expert in Python/Django Framework. 3. Algorithm: Expert in Machine Learning and Data Intelligence. | OJT | AM - Digr | Accenture - AM | 2015-12-21 | 2016-02-28 | Confirm with wujiong. Leave vacation from 28 Dec,2015 to 4 Jan,2016 | Shanghai | 11082411 | 15026929959 | Fu, William Yong
Mao, Allison Yunhui | yunhui.mao@accenture.com | SSE | Html5, JS |  |  | Familiar with JS, Expert in Html5 | OJT | AM - Digr | Accenture - AM | 2015-12-21 | 2016-02-28 | Leave vacation from 24 Dec,2015 to 4 Jan,2016 | Shanghai | 10993500
Wang, Daisy Weihong | weihong.wang@accenture.com | SSE | Html5 |  |  | Expert in Html5, understand JS | OJT | AM - Digr | Accenture - AM | 2015-12-21 | 2016-02-28 | Leave vacation from 24 Dec,2015 to 4 Jan,2016 | Shanghai | 11009989 | 13962247632 | Tang, Wendy Wenjing
Jiang, Xujing | xujing.jiang@accenture.com | SE | Html5 |  |  | Familiar with Html5, understand JS/Angular JS/Ionic | OJT | AM - Digr | Accenture - AM | 2015-12-21 | 2016-02-28 | Leave vacation from 28 Dec,2015 to 4 Jan,2016 | Shanghai | 11090383 | 15300621569 | Tang, Wendy Wenjing
Liu, Liu | liu.a.liu@accenture.com | ASE | Html5, JS |  |  | Familiar with Html5, understand JS/Jquery | OJT | AM - Digr | Accenture - AM | 2015-12-21 | 2016-02-28 | Leave vacation from 28 Dec,2015 to 4 Jan,2016 | Shanghai | 11148696 | 13872425730 | Zhu, Linda Xiaolin
Hu, Dandan | dandan.hu@accenture.com | ASE | Html5, JS |  |  |  | Hardlock | dLife | Accenture - Digital |  |  | Leave vacation from 24 Dec,2015 to 25 Dec,2015 Backup: Tang, Wenjing | Shanghai | 11145564 | 18817393049 | Zhu, Linda Xiaolin
Zhang, Huaifei | huaifei.zhang@accenture.com | ASE | Html5, JS |  |  |  | Hardlock | dLife | Accenture - Digital |  |  |  | Shanghai | 11145582 | 18217043897 | Zhu, Linda Xiaolin
Lu, Guangwei | guangwei.lu@accenture.com | ASE | Html5, JS |  |  | Bench, still work on dLife. | OJT |  |  |  |  | Share Evan's code to them Leave vacation from 28 Dec,2015 to 4 Jan,2016 | Shanghai | 11148689 | 15123077273 | Zhu, Linda Xiaolin
Huang, Yun | yun.huang@accenture.com | ASE | Html5, JS |  |  |  | Hardlock | O2O | Accenture - Digital |  |  |  | Shanghai | 11145561 | 18817353831 | Zhu, Linda Xiaolin
Wang, Kena | kena.wang@accenture.com | ASE | Html5, JS |  |  |  | Hardlock | O2O | Accenture - Digital |  |  |  | Shanghai | 11147835 | 15224048187 | Zhu, Linda Xiaolin
Chen, Lihui | lihui.chen@accenture.com | ASE | Html5, JS |  |  |  | Hardlock | 年会项目 | Accenture - Digital | 2015-12-15 | 2016-01-12 |  | Shanghai | 11145550 | 15618683553 | Tang, Wendy Wenjing
Zhou, Miao | miao.zhou@accenture.com | SE | Html5 |  |  |  | OJT |  |  |  |  | Leave vacation from 28 Dec,2015 to 4 Jan,2016 假期-24hours，年会项目无code | Shanghai | 11090103 | 17091832586 | Tang, Wendy Wenjing
Hua, Chenxing | chenxing.hua@accenture.com | ASE | Html5, JS |  |  |  | Future Hardlock | CIO - Asset | Accenture - CIO |  |  | 假期-60hours | Shanghai | 11148683 | 13611907439 | Zhu, Linda Xiaolin
Dong, Jiawei | jiawei.dong@accenture.com | ASE | Html5, JS |  |  |  | Hardlock | AM - Digr | Accenture - AM | 2015-12-21 | 2016-02-28 |  | Shanghai | 11145555 | 13795369618 | Zhu, Linda Xiaolin
Hao, Junyu | junyu.hao@accenture.com | ASE | Html5, JS | Photoshop |  | Familiar with Photoshop, understand Illustrator.(Familiar with Html5, understand JS/Jquery). | Hardlock | 年会项目 |  | 2015-12-15 | 2016-01-12 |  | Shanghai | 11145559 | 15201733231 | Sun, Tina Yanting
Wang, Kena | kena.wang@accenture.com | ASE | Html5, JS |  |  |  | Hardlock | O2O | Accenture - Digital |  |  |  | Shanghai | 11147835 | 15224048187 | Zhu, Linda Xiaolin
Lu, Jing | jing.a.lu@accenture.com | SE | Html5 |  |  |  | Parent Leave | [5 empty] | Shanghai | 11090034
Zeng, Mubin | mubin.zeng@accenture.com | TL | Html5, JS/JQuery | Photoshop, AxurePro, Painting | 6 | Expert in Photoshop & AxurePro, familiar with Illustrator, understand AE, Justinmind, 3D MAX, Indesign, Painting. Experienced with mobility, responsive design. | OJT | [5 empty] | Guangzhou | 11116180 | 15902048810 | Zeng, Mubin
He, Nico Zhengli | zhengli.he@accenture.com | SE |  | Photoshop, Painting | 3 | Familiar with Photoshop & Illustrator, understand Painting. | Hardlock | 信息化建设与大数据整合项目 | 兖矿集团 | 12-20-2015 | 1-15-2016 |  | Guangzhou | 11138934 | 18565561615 | Zeng, Mubin
Liu, Jie | jie.c.liu@accenture.com | SE |  | Photoshop, AxurePro, Painting | 3 | Familiar with Photoshop & Illustrator, understand CDR, Painting , AxurePro, Premier, AE. Experienced with mobility. | Hardlock | Towngar | 香港中华燃气 | 12-21-2015 | 1-31-2016 |  | Guangzhou | 11118653 | 13286337705 | Zeng, Mubin
Gai, Gavin Jiachuan | jiachuan.gai@accenture.com | SE |  | Photoshop, Painting | 2 | Familiar with Photoshop & Flash, understand AE, Premier, Maya, Illustrator Painting. | OJT | Unicharm | Unicharm |  |  |  | Guangzhou | 11166672 | 18642847927 | Zeng, Mubin
Cai, Fan | fan.cai@accenture.com | SE |  | Photoshop, Painting | 3 | Familiar with Photoshop, understand Flash, Premier, AE, Illustrator, Painting. Experienced with mobility. | OJT | [5 empty] | Guangzhou | 11117026 | 13711288297 | Zeng, Mubin
Ou, Lijie | lijie.ou@accenture.com | SE | Html5, JS/JQuery | Photoshop, AxurePro, Painting | 3 | Familiar with Photoshop, Illustrator, AxurePro, undertand Flash & Painting. Experienced with Mobility, Responsive Design. | OJT | [5 empty] | Guangzhou | 11116180 | 13726776987 | Zeng, Mubin
Liu, Krystal Jiaxin | jiaxin.liu@accenture.com | SE |  | Photoshop, Painting | 3 | Familiar with Photoshop, CDR, Rhino, Keyshot, AE, Painting, undertand Illustrator & Indesign. Experienced with Mobility. | OJT | [5 empty] | Guangzhou | 11122066 | 18825181010 | Zeng, Mubin
Chen, Johnny Zhaoqiang | zhaoqiang.chen@accenture.com | SE |  | Photoshop, Painting | 2 | Familiar withPhotoshop & Illustrator, understand Indesign, Painting, Flash, AE. Experienced with Mobility. | OJT | [5 empty] | Guangzhou | 11159095 | 13533888160 | Zeng, Mubin
Guo, Yuhui | yuhui.guo@accenture.com | SSE | Html5, JS |  |  |  | OJT | [5 empty] | Guangzhou | 11104442 | 13580388273 | Zeng, Mubin
Zhao, Chunsen | chunsen.zhao@accenture.com | SSE | Html5, JS |  |  |  | OJT | [5 empty] | Guangzhou | 11104443 | 18319984205 | Zeng, Mubin
Wu, Baofeng | baofeng.wu@accenture.com | SSE | Html5, JS |  |  |  | Hardlock | iBank Execution Phase IT_SI | iBank | 12-28-2015 | 6-31-2016 |  | Dalian | 11160071 | 18640819927 | Yu, Josh Peng
Liu, Xinyi | xinyi.liu@accenture.com | SSE |  |  |  |  | Hardlock | CIO 003 - MMC | Accenture - CIO |  |  |  | Dalian | 11153428
Zhang, Wei | wei.g.zhang@accenture.com | TL |  |  |  |  | Hardlock | CIO 003 - MMC | Accenture - CIO |  |  |  | Dalian | 11148147
Du, Tony Wenbin | wenbin.du@accenture.com | TL | Html5, JS/AngularJS |  |  | Expert in JS/Angular, Familiar with Html5 |  | MMC Team 4 & Team 5 | Accenture - CIO |  |  |  | Dalian | 11165379 | 18698745350 | Du, Tony Wenbin
Li, Linchun | linchun.li@accenture.com | SSE | Html5, JS/AngularJS |  |  | Familiar with Html5, JS/Angular JS | Future Hardlock | CIO 003 - MMC | Accenture - CIO | 1-18-2016 | 8-31-2016 | 推荐到对日项目，没有具体上项目时间 | Dalian | 11087478 | 18640817102 | Yu, Josh Peng
Yu, Josh Peng | p.yu@accenture.com | AM | Html5, JS/AngularJS |  |  |  | Hardlock | CIO 001 | Accenture - CIO | 2015-12-14 | 2016-08-31 | 已进华为项目 | Dalian | 11183596 | 15941101026 | Yu, Josh Peng
Zhang, Sailor Xiangnan | xiangnan.zhang@accenture.com | SSE | Html5, JS/AngularJS |  |  |  | Hardlock | CIO 001 | Accenture - CIO | 2015-12-21 | 2016-08-31 |  | Dalian | 11160972 | 15840936229 | Du, Tony Wenbin
Li, Gavin Zhichao | zhichao.li@accenture.com | SSE | Html5, JS/AngularJS |  |  |  | Hardlock | CIO 001 | Accenture - CIO | 2015-12-21 | 2016-08-31 |  | Dalian | 11161760 | 15140309680 | Du, Tony Wenbin
Jiao, Wenzhi | wenzhi.jiao@accenture.com | SE | Html5, JS/AngularJS |  |  |  | OJT | CIO 001 |  |  |  | 预计1月2号上ICO项目 | Dalian | 11161763 | 15140317885 | Yu, Josh Peng
Jia, Yuzhuo | yuzhuo.jia@accenture.com | ASE | Html5, JS |  |  |  | Hardlock | Janpanese Android |  | 12-21-2015 | 8-31-2016 |  | Dalian | 11154869 | 13624240332 | Yu, Josh Peng
Zhang, Yao | yao.b.zhang@accenture.com | ASE | Html5, JS |  |  |  | OJT | [5 empty] | Dalian | 11154886 | 13237086320 | Du, Tony Wenbin
Liu, Danyu | danyu.liu@accenture.com | ASE | Html5, JS |  |  |  | Hardlock | Janpanese Android |  | 1-12-2016 | 3-31-2016 |  | Dalian | 11154860 | 13624286264 | Du, Tony Wenbin
Wang, Weiqi | weiqi.a.wang@accenture.com | ASE | Html5, JS |  |  |  | OJT | [5 empty] | Dalian | 11154869 | 18642866302 | Yu, Josh Peng
Yang, Donghui | donghui.yang@accenture.com | ASE | Html5, JS |  |  |  | OJT | [5 empty] | Dalian | 11154852 | 13664141025 | Du, Tony Wenbin
Zhang, Xuanwei | xuanwei.zhang@accenture.com | ASE | Html5, JS |  |  | Familiar with Html5, understand JS/Angular JS | [6 empty] | Dalian | 11154858 | 13591735568 | Yu, Josh Peng
Lv, Dage | dage.lv@accenture.com | TL | Html5, JS/AngularJS |  |  | Familiar with Html5, expert in JS/Angular JS | Hardlock | NTP |  | 1-4-2015 | 8-31-2016 |  | Dalian | 11163253 | 13079889935 | Yu, Josh Peng

## 工作表1
Project | E.ID | Employer Name | Status | Name | Status | Comments
SAP Fiori - Onshore | minmin.sun@accenture.com | Zhao, Chunsen | IOT项目 无code | Sun, Tina Yanting | Vacation | Leave vacation from 28 Dec,2015 to 4 Jan,2016
SAP Fiori - Onshore | l.a.ma@accenture.com | Guo, Day Yuhui | IOT项目 无code | Zhang, Miao | Vacation | Leave vacation from 28 Dec,2015 to 4 Jan,2016
SAP Fiori - Onshore | ying.qu@accenture.com | Zeng, Mubin | 年会节目，年会前期准备，UIUX宣传册 | Hou, Ming | Vacation | Leave vacation from 28 Dec,2015 to 4 Jan,2016
SAP Fiori - Onshore | wenjing.tang@accenture.com | Li, Linchun | 自学AngularJS | Fan, Yang | Vacation | Leave vacation from 28 Dec,2015 to 4 Jan,2016
SAP Fiori - Onshore | x.qian@accenture.com | Zhang, Miao | 筹备年会网站 | Fu, William Yong | Vacation | Leave vacation from 28 Dec,2015 to 4 Jan,2016
SAP Fiori - Onshore | yao.feng@accenture.com | Du, Tony Wenbin | 带ASE培训AngularJS | Mao, Allison Yunhui | Vacation | Leave vacation from 24 Dec,2015 to 4 Jan,2016
SAP Fiori - Onshore | xueliang.deng@accenture.com | Wang, Daisy Weihong | 自学JS | Wang, Daisy Weihong | Vacation | Leave vacation from 28 Dec,2015 to 4 Jan,2016
SAP Fiori - Onshore | xiaonan.d.wang@accenture.com | Chen, Johnny Zhaoqiang | UIUX宣传册 | Jiang, Xujing | Vacation | Leave vacation from 28 Dec,2015 to 4 Jan,2016
SAP Fiori - Onshore | hongxia.huang@accenture.com | Liu, Krystal Jiaxin | UIUX宣传册 | Liu, Liu | Vacation | Leave vacation from 28 Dec,2015 to 4 Jan,2016
SAP Fiori - Onshore | hui.shi@accenture.com | Cai, Fan | 自学AE | Hu, Dandan | Vacation | Leave vacation from 24 Dec,2015 to 25 Dec,2015 Backup: Tang, Wenjing
SAP Fiori - Onshore | chenqing.gu@accenture.com | Ou, Lijie | 年会前期准备 | Lu, Guangwei | Vacation | Leave vacation from 28 Dec,2015 to 4 Jan,2016
SAP Fiori - Onshore | fang.ni@accenture.com | Mao, Allison Yunhui | 产假刚回来 | Zhou, Miao | Vacation | Leave vacation from 28 Dec,2015 to 4 Jan,2016
BMW CN.DIGITAL | mingming.ying@accenture.com | Fu, William Yong | BD-四联创业化工 | Zhou, Wang | Vacation | 假期-64hours
BMW CN.DIGITAL | yunjie.ping@accenture.com | Jiang, Xujing | 自学AngularJS | Hua, Chenxing | Vacation | 假期-60hours
BMW CN.DIGITAL | ping.jiang@accenture.com | Zhou, Miao | 筹备年会网站
L’orealParis | xiaolin.zhu@accenture.com | Fan, Yang | 自学AngularJS
BMS Responsive Design | yanting.sun@accenture.com | Kan, Jiangtao | 筹备年会网站
BMS Responsive Design | jiangtao.kan@accenture.com | Sun, Tina Yanting | BD-四联创业化工，年会前期准备，UIUX宣传册，UIUX成员动向跟踪
BMS Responsive Design | miao.c.zhang@accenture.com
Accenture - dLife | dandan.hu@accenture.com
Accenture - dLife | huaifei.zhang@accenture.com
Accenture - dLife | guangwei.lu@accenture.com
Accenture - O2O | yun.huang@accenture.com
Accenture - O3O | kena.wang@accenture.com
Accenture - CIO | ming.hou@accenture.com
Accenture - CIO | shenglei.hua@accenture.com
Accenture - MMC Team 3 | tianwen.dong@accenture.com
Accenture - MMC Team 4 & Team 5 | yang.fan@accenture.com
CIO - Asset | m.a.han@accenture.com
CIO - Asset | wang.a.zhou@accenture.com
CIO - Asset | liu.a.liu@accenture.com
AM - Asset | yong.fu@accenture.com
AM - Asset | yunhui.mao@accenture.com
AM - Asset | weihong.wang@accenture.com
AM - Asset | xujing.jiang@accenture.com
AM - Asset | jintao.xiao@accenture.com
OJT | lihui.chen@accenture.com
OJT | miao.zhou@accenture.com
OJT | chenxing.hua@accenture.com
OJT | jiawei.dong@accenture.com
OJT | junyu.hao@accenture.com
OJT | hongjian.wu@accenture.com